## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2021-09-06 | 7 | 2021-09-12 | 38 | 5 | Ongoing | 2021-09-13 | Sprint 0: Documentación y gestión del proyecto | 13.16%
2 | 2021-09-13 | 7 | 2021-09-19 | 0 | 0 | Unplanned | 2021-09-20 | Sprint 1 y 2: Interfaz gráfica del MVC (HTML, CSS y Javascript) | #DIV/0!
3 | 2021-09-20 | 7 | 2021-09-26 |  |  | Unplanned | 2021-09-27
4 | 2021-09-27 | 7 | 2021-10-03 |  |  | Unplanned | 2021-10-04
5 | 2021-10-04 | 7 | 2021-10-10 |  |  | Unplanned | 2021-10-10
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
1 | 2021-09-06 | 7 | 2021-09-12 | 2 | 3 | Released | 2021-09-13 | Product Backlog priorizado | 1 | 50%
1 | 2021-09-06 | 7 | 2021-09-12 | 6 |  | Ongoing | 2021-09-13 | Generación documentación | 1 | -100%
1 | 2021-09-06 | 7 | 2021-09-12 | 1 | 1 | Released | 2021-09-13 | Creación repositorio y envio invitacion colaboradores. | 1 | 0%
1 | 2021-09-06 | 7 | 2021-09-12 | 1 | 1 | Released | 2021-09-13 | Gestion de configuración | 1 | 0%
1 | 2021-09-06 | 7 | 2021-09-12 | 16 |  | Ongoing | 2021-09-13 | Historias de usuario | 1 | -100%
1 | 2021-09-06 | 7 | 2021-09-12 | 4 |  | Ongoing | 2021-09-13 | Configuración GitHub Proyecto | 1 | -100%
1 | 2021-09-06 | 7 | 2021-09-12 | 8 |  | Ongoing | 2021-09-13 | Mockups | 1 | -100%
| 2021-09-13 |  |  |  |  | Unplanned
3 | 2021-09-20 |  |  | #VALUE! |  | Unplanned
4 | 2021-09-27 |  |  | #VALUE! |  | Unplanned
5 | 2021-10-04 |  |  | #VALUE! |  | Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | #VALUE!
|  |  | Total Size | #VALUE! | 5
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")
Release Date = [Start, row below]
Release Date = [End]

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Product Backlog priorizado | Planned | 2 | 1 | 1 | Desarrollo | Se listan las actividades hasta el sprint 1.
2 | Generación documentación | Planned | 6 | 1 | 1 | Desarrollo
3 | Creación repositorio y envio invitacion colaboradores. | Planned | 1 | 1 | 1 | Desarrollo | Enlace: https://github.com/lufermaxi/ProyectoBibliotech
4 | Gestion de configuración | Planned | 1 | 1 | 1 | Desarrollo | Se modifica el Pdf de la plataforma
5 | Historias de usuario | Planned | 16 | 1 | 1 | Desarrollo | Las historias de usuario se desarrollan en un doc que se encuentra en el drive.
6 | Configuración GitHub Proyecto | Planned | 4 | 1 | 1 | Desarrollo | Se crea el tablero de tareas, etiquetas y Milestones para identificar los sprints.
7 | Mockups | Planned | 8 | 1 | 1 | Desarrollo
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.